## Summary Page
STUDY Close Out Summary
TM-T24 v3.0
Close Out Milestones | Date / Target Date | Days remaining | Progress | Complete | Comments | Site Close Out Overview | Site 1 | Site 2 | Site 3 | Site 4 | Site 5 | Site 6 | Keys:
Database Lock |  |  | On track |  |  | Status | [7 empty] | Close Out Pending
All Sites Closed |  |  | On track |  |  | Date of Last Contact | [7 empty] | In Progress
End of Trial Form |  |  | On track |  | Must be submitted within 90 days of end of trial or 15 days of premature end of trial | Main Site Contact | [7 empty] | Closed
Grant End |  |  | On track |  |  | Comments
Final Study Report |  |  | On track |  | Post-grant unfunded | [8 empty] | Yes
Archiving Complete |  |  | On track |  | Post-grant unfunded | [8 empty] | No
Progress | Comments | [12 empty] | 31
Pre-Close Out Prep | [13 empty] | 30 | Due Soon
Site Close Out | [13 empty] | -1 | Overdue
Pharmacy Close Out
Imaging
Samples
IMP
Lab
Safety
Data
Finance
Regulatory
Study Close Out
Formulas:
Days remaining = IF(OR([Date / Target Date]="", [Complete]="Yes"), "", [Date / Target Date]-TODAY())
Progress = IF([Complete]="Yes", "On track", IF(COUNTIF([Date / Target Date]:B9, "<"&TODAY())>0, "Final deadline at risk", "On track"))
This tracker should be customised for your study - add or remove lines/columns as required. In the next tab, use colour to highlight what is missing/ongoing/complete. Do not leave blank white cells.
Ongoing pre-close out meetings/discussions with sponsor/monitors/ stats/DM/HE/TMG are recommended.
Note on F3: e.g. to note funder requirements for the final report (e.g BHF final report needs to be submitted within 3 months of end date).
Note on I5: You do not need to manually add dates, this row has a formula to pull the data from the close out tracker
Note on A6: CTIMP: found on MHRA website https://www.gov.uk/guidance/clinical-trials-for-medicines-manage-your-authorisation-report-safety-issues#end-of-trial Non-CTIMP: found on HRA websitehttp://www.hra.nhs.uk/resources/during-and-after-yourstudy/end-of-study-notification-studies-other-than-clinical-trials-ofinvestigational-medicinal-products/.

## Close Out Tracker
STUDY NAME | Priority | Study | Site 1 | Site 2 | Site 3 | Site 4 | Site 5 | Site 6
Delete and add rows/columns as necessary for your study | [8 empty] | TM-T24 v3.0
Pre-Close Out Preparations
Arrange a End of Trial Meeting |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Draft End of Trial Meeting Agenda |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Circulate Minutes from the End of Trial Meeting |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Draft Project Closure Plan |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Project Closure Plan Approved |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Site Close Out
Date of Last Contact
LPLV
Notify R&Ds and Site: Recruitment Closed
Initial Close Out Contact
ISF Essential Documents Sent to Site
Missing ISF Documents Sent to Site
ISF Essential Documents Complete
Missing Documents for TMF received
Final Training Log Received
Updated Delegation Log Received
Training Log Review Complete
CV/GCP TMF Check Complete
CV/GCP Training Tracker Finalised
COV Checklist Sent to Site
COV Checklist Returned
Pre-Screening/ Screening Log Complete
CPMS Accurate and Complete
COV Checklist Reviewed
Pre-Close Out Call Arranged (if necessary)
COV Booked
COV Complete
COV Report Sent to Monitor
COV Report, COV Letter & Action Log Sent to Site
Final Delegation Log Received
COV Actions Complete
Final Close Out Letter Sent to Site & R&D
Notify R&Ds of EoS
Pharmacy Close Out
PSF Checklist Sent to Site
Missing PSF Docs Sent to Site
COV Checklist Sent to Site
Inventory Logs Received
Accountability Logs Received
Logs Sent to Monitor for Review
Sponsor Approval for Destruction of Remaining IMP Received
Destruction Log/Certificate Received
Destruction Log/Certificate Sent To Sponsor
Pharmacy COV Booked
Pharmacy COV Complete
Pharmacy COV Checklist Complete
IMP Destruction Confirmation sent to IMP supplier
IMP Tracker Finalised
Imaging
All Images Uploaded
All Image Queries Resolved
Imaging Quality Sufficient
Adjudication complete (if applic)
Samples
Email Sites Sample Collection Preparation and Instructions
Samples Ready for Collection at Site
Courier Quote Requested
Sample Logs Received
Courier Booked
Samples Received at XX
Sample Analysis Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Results Sent to Site
Sample Analysis Results Uploaded to the Database
IMP
Notify IMP supplier of EoS |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Remaining IMP destroyed |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Lab
Lab Accreditation Certificates Received
Lab Reference Ranges Received
Lab Costs Paid
Safety
AEs/SAEs Complete
Meddra Coding Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Submit final DSUR to MHRA |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Deviation Logs Complete
Violation Reports Completed
Pharmacovigilance team made aware of DB lock date |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Request Final Listings from Sponsor |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final AE/SAE Reconciliation
Final Deviation Reconciliation
Final Violation Reconciliation
Deviation/Violation Tracker Finalised |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Data
Recruitment Function on DB Blocked |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Missing Data recorded as a deviation
Data Cleaning Plan Finalised by DM Team |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Sites Made Aware of DB cleaning & DB Lock Timelines & Responsibilites
Population Definitions Agreed with Stats |  |  | N/A | N/A | N/A | N/A | N/A | N/A
SAP Finalised & Signed |  |  | N/A | N/A | N/A | N/A | N/A | N/A
HEAP Finalised and Signed |  |  | N/A | N/A | N/A | N/A | N/A | N/A
DB Entry Complete
e-screening Log Complete if applic
DB Queries Closed
Data Ready for Stats Review |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Stats DB Queries Completed |  |  | N/A | N/A | N/A | N/A | N/A | N/A
PI Declaration of CRF Complete
Data Ready for Sponsor Review |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Sponsor approval to lock Database |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Site DB Access Removed & CV/GCP training tracker updated
Final Data QC Check Performed |  |  | N/A | N/A | N/A | N/A | N/A | N/A
DB Lock Checklist Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
ECTU team DB access removed or read only |  |  | N/A | N/A | N/A | N/A | N/A | N/A
DB Lock Approval Received from Stats |  |  | N/A | N/A | N/A | N/A | N/A | N/A
DB Locked |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Centrally Collected Participant Data Shared with Sites
Receipt of Centrally Collected Participant Data Shared by Site
Finance
Site Invoices Paid & tracker updated
Collaborator Invoices Paid
Courier and Sample Shipments Invoices Paid
PO Requested for Archiving |  |  | N/A | N/A | N/A | N/A | N/A | N/A
PO requested for Publication Costs |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Finance tracker finalised |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final Reconciliation of Grant |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Regulatory
Notify Sponsor of EoS |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Notify MHRA/ Cas of EoS |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Notify RECs of EoS |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Amendment to Protocol (if early closure) |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Study Close Out
Central Delegation Log Signed Off (if applic) |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final TMF Review & monitoring actions complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
CONSORT Diagram Finalised |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Validation of HE Analysis |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Statistics Analysis Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Validation of statistical Analysis |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Health Economics Analysis Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final DMC |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final TSC |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final Study Report Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final Report Submitted to Funder |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Final Report Submitted to RECs |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Trial Collaboration Document is complete and approved |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Dissemination of Results |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Reporting (EudraCT, clinical trials.gov, ISRCTN) |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Website(s) updated with status and lay summary |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Study level close out checklist CM003-T04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Project Closure Plan Updated |  |  | N/A | N/A | N/A | N/A | N/A | N/A
TMF Archived |  |  | N/A | N/A | N/A | N/A | N/A | N/A
Key
HIGH
MEDIUM
LOW
Note on A4: Invite: TM, CI, Statistican, Sponsor Rep (if applicable), Data Management/Programmer & any other relevant trial team
Note on A5: TM-TM28 Topics to include: End of trial notifications Data cleaning Database lock Final DMC and/or TSC Publication and dissemination of results
Note on A7: OP-T05 Should be circulated for review to applicable teams at least 6 months before end of grant date. If early closure should be in place asap.
Note on A8: Senior TMs, CI and other relevant trial team should approve the plan before it is finalised. Ensure ongoing actions from PCP are added to this close out tracker.
Note on A11: Check protocol wording as this should be defined i.e., last IMP, last questionnaire
Note on A17: i.e., R&D/C&C approvals, localised documents, PI signature pages
Note on A23: CM003-T03
Note on A25: Ensure this matches what the site report in the COV checklist
Note on A26: Ensure you contact Fiona (CPMS contact) to move study status to complete
Note on A27: Please review no. of participants screened, recruited, no. of deviations, no. of AEs etc that site report on the form compared to central records (database)
Note on A31: CM003-T02
Note on A32: COV Letter CM003-T06 Action Log (CM003-T05)
Note on A33: Do not request the final delegation log until you are sure all actions from site are complete
Note on A35: CM003-T08 Wait until database lock is complete as sites may have queries to address Site now has approval to archive
Note on A42: If you have a ward level accountability ward also request this
Note on A58: Consider timelines for samples being returned and analysed. Do the results need to be added to the database before it is locked, can the sites meet the deadline you set?
Note on A68: If the study finishes early you will need to make the IMP supplier aware
Note on A69: if you have left over IMP you will need to contact the supllier to destroy this and it may come with an additional cost
Note on A76: Create a filenote to document the version of MedDRA coding used
Note on A88: i.e., missed follow ups, missed questionnaires etc
Note on A97: Must be at least 2 weeks before planned database lock
Note on A100: Must be at least 2 weeks before planned database lock
Note on A106: Should email TM, CI, DM team & sponsor
Note on A107: DM&P team should email trial inbox and CI confirmation
Note on A108: i.e., centrally collected consent forms and centrally collected follow up data
Note on A136: Ensure this document is complete prior to publication and that the CI has approved.
Note on A137: Ensure there is a plan in place for how to disseminate the trial results with participants, sites, the rest of ECTU etc
Note on A141: Add completion dates to tasks before handing over study