## Study Overview
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 08/02/2024
[Trial Name] | Target recruitment number |  |  | 300
MILESTONE | Grant | Extension (agreed with funder) | Estimate | Adjusted Estimate | Actual
Grant start date
Sponsor Review & Risk Assessment | Not specified
REC Approvals in place | Not specified
MHRA Approvals in place | Not specified
First SIV | Not specified
Last SIV | Not specified | [7 empty] | [Trial Name] Recruitment
First Site Open | [5 empty] | Project Month | Project Milestone (Original) | Recruitment | Grant Projected randomised | Grant Projected randomised (%) | Expected randomised by feasibility (Original) | Expected randomised by feasibility (%) | Expected randomised (Adjusted Extension) | Actual randomised | Actual randomised (%) | Grant Projected completed | Grant Projected completed (%) | Expected completed by feasibility (Original) | Expected completed by feasibility (%) | Expected completed (Adjusted Extension) | Actual completed | Actual completed (%) | Withdrawn* | Withdrawn - Data Deleted
FPFV/Recruitment start date | [5 empty] | 7 | FPFV/Recruitment start date | Jan 202X | 0 | 0% | 0 | 0% | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 0 | 0% | 0 | 0
Last Site Open | [5 empty] | 8 | FPFV/Recruitment start date | Feb 202X | 0 | 0% | 3 | 1% | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 0 | 0% | 0 | 0
Stop/Go Criteria: | [5 empty] | 9 |  | Mar 202X | 3 | 1% | 7 | 2.333% | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 0 | 0% | 0 | 0
50% of recruitment | [5 empty] | 10 | FPFV/Recruitment start date | Apr 202X | 7 | 2.333% | 12 | 4% | 9 | 7 | 2.333% | 0 | 0% | 0 | 0% | 9 | 0 | 0% | 0 | 0
Recruitment end date (LPFV) | [5 empty] | 11 |  | May 202X | 12 | 4% | 19 | 6.333% | 13 |  | 0% | 0 | 0% | 0 | 0% | 13 |  | 0%
LPLV | [5 empty] | 12 |  | Jun 202X | 19 | 6.333% | 28 | 9.333% | 18 |  | 0% | 0 | 0% | 4 | 1.333% | 18 |  | 0%
Follow-up end date | [5 empty] | 13 |  | Jul 202X | 28 | 9.333% | 38 | 12.67% | 25 |  | 0% | 3 | 1% | 14 | 4.667% | 25 |  | 0%
Database Lock | Not specified |  |  |  |  | 14 |  | Aug 202X | 38 | 12.67% | 49 | 16.33% | 33 |  | 0% | 7 | 2.333% | 20 | 6.667% | 33 |  | 0%
Data Analysis & Report Completed | Not specified |  |  |  |  | 15 |  | Sep 202X | 49 | 16.33% | 59 | 19.67% | 44 |  | 0% | 12 | 4% | 31 | 10.33% | 44 |  | 0%
Final study report | [5 empty] | 16 |  | Oct 202X | 59 | 19.67% | 70 | 23.33% | 54 |  | 0% | 19 | 6.333% | 37 | 12.33% | 54 |  | 0%
Grant end date | [5 empty] | 17 |  | Nov 202X | 70 | 23.33% | 81 | 27% | 65 |  | 0% | 28 | 9.333% | 48 | 16% | 65 |  | 0%
[6 empty] | 18 | Stop/Go Criteria: 80 pts | Dec 202X | 81 | 27% | 92 | 30.67% | 75 |  | 0% | 38 | 12.67% | 54 | 18% | 75 |  | 0%
Updated xx/xx/202x | [5 empty] | 19 |  | Jan 202X | 92 | 30.67% | 102 | 34% | 86 |  | 0% | 49 | 16.33% | 65 | 21.67% | 86 |  | 0%
[6 empty] | 20 | Stop/Go Criteria: 80 pts | Feb 202X | 102 | 34% | 114 | 38% | 98 |  | 0% | 59 | 19.67% | 72 | 24% | 98 |  | 0%
[6 empty] | 21 |  | Mar 202X | 114 | 38% | 125 | 41.67% | 107 |  | 0% | 70 | 23.33% | 83 | 27.67% | 107 |  | 0%
[6 empty] | 22 |  | Apr 202X | 125 | 41.67% | 136 | 45.33% | 119 |  | 0% | 81 | 27% | 90 | 30% | 119 |  | 0%
[6 empty] | 23 | 50% of recruitment | May 202X | 136 | 45.33% | 146 | 48.67% | 131 |  | 0% | 92 | 30.67% | 101 | 33.67% | 131 |  | 0%
[6 empty] | 24 | 50% of recruitment | Jun 202X | 146 | 48.67% | 156 | 52% | 141 |  | 0% | 102 | 34% | 111 | 37% | 141 |  | 0%
[6 empty] | 25 |  | Jul 202X | 156 | 52% | 165 | 55% | 152 |  | 0% | 114 | 38% | 122 | 40.67% | 152 |  | 0%
[6 empty] | 26 | 50% of recruitment | Aug 202X | 165 | 55% | 173 | 57.67% | 162 |  | 0% | 125 | 41.67% | 132 | 44% | 162 |  | 0%
[6 empty] | 27 |  | Sep 202X | 173 | 57.67% | 183 | 61% | 171 |  | 0% | 136 | 45.33% | 143 | 47.67% | 171 |  | 0%
[6 empty] | 28 |  | Oct 202X | 183 | 61% | 195 | 65% | 179 |  | 0% | 146 | 48.67% | 153 | 51% | 179 |  | 0%
[6 empty] | 29 |  | Nov 202X | 195 | 65% | 207 | 69% | 188 |  | 0% | 156 | 52% | 164 | 54.67% | 188 |  | 0%
[6 empty] | 30 |  | Dec 202X | 207 | 69% | 218 | 72.67% | 200 |  | 0% | 165 | 55% | 174 | 58% | 200 |  | 0%
[6 empty] | 31 |  | Jan 202X | 218 | 72.67% | 228 | 76% | 212 |  | 0% | 173 | 57.67% | 185 | 61.67% | 212 |  | 0%
[6 empty] | 32 |  | Feb 202X | 228 | 76% | 240 | 80% | 224 |  | 0% | 183 | 61% | 195 | 65% | 224 |  | 0%
[6 empty] | 33 |  | Mar 202X | 240 | 80% | 252 | 84% | 233 |  | 0% | 195 | 65% | 206 | 68.67% | 233 |  | 0%
[6 empty] | 34 |  | Apr 202X | 252 | 84% | 264 | 88% | 245 |  | 0% | 207 | 69% | 216 | 72% | 245 |  | 0%
[6 empty] | 35 |  | May 202X | 264 | 88% | 274 | 91.33% | 257 |  | 0% | 218 | 72.67% | 227 | 75.67% | 257 |  | 0%
[6 empty] | 36 |  | Jun 202X | 274 | 91.33% | 283 | 94.33% | 269 |  | 0% | 228 | 76% | 237 | 79% | 269 |  | 0%
[6 empty] | 37 |  | Jul 202X | 283 | 94.33% | 292 | 97.33% | 280 |  | 0% | 240 | 80% | 248 | 82.67% | 280 |  | 0%
[6 empty] | 38 | Recruitment end date | Aug 202X | 292 | 97.33% | 300 | 100% | 289 |  | 0% | 252 | 84% | 258 | 86% | 289 |  | 0%
[6 empty] | 39 | Recruitment end date | Sep 202X | 300 | 100% |  | 0% | 298 |  | 0% | 264 | 88% | 269 | 89.67% | 298 |  | 0%
[6 empty] | 40 | Recruitment end date | Oct 202X |  | 0% |  | 0% | 306 |  | 0% | 274 | 91.33% | 279 | 93% | 306 |  | 0%
[6 empty] | 41 |  | Nov 202X |  | 0% |  | 0% | 306 |  | 0% | 283 | 94.33% | 290 | 96.67% | 306 |  | 0%
[6 empty] | 42 | Follow-up end date | Dec 202X |  | 0% |  | 0% | 306 |  | 0% | 292 | 97.33% | 300 | 100% | 306 |  | 0%
[6 empty] | 43 |  | Jan 202X |  | 0% |  | 0% | 306 |  | 0% | 300 | 100% |  | 0% | 306 |  | 0%
[6 empty] | 44 | Follow-up end date | Feb 202X |  | 0% |  | 0% | 306 |  | 0% |  | 0% |  | 0% | 306 |  | 0%
[6 empty] | 45 |  | Mar 202X |  | 0% |  | 0% | 306 |  | 0% |  | 0% |  | 0% | 306 |  | 0%
* Data from patients retained for analysis up to the point of withdrawal.
SUMMARY:
1. Complete the overview of study milestones and recruitment target on 'Study Overview' tab first and adjust dates on recruitment overview table.
2. Complete 'Gantt chart'. Remember to keep modifying this as the study progresses.
3. Modify number of sites/timeline and complete estimated recruitment based on feasiblity/site agreement numbers on 'Projected Feasibility Recruitment' tab.
OPTIONAL: Modify number of sites/timeline on 'Grant Projected recruitment' tab depending on detail of requirements from your funder.
3.Modify number of sites/timeline and enter real recruitment values monthly on the 'Actual recruitment by site' tab. Add SATO dates for each site to see average recruitment per month.
OPTIONAL: Screening/washout numbers can also be tracked on the 'Screening_Washout' tab.
4. Modify number and name of sites/timeline and review estimated vs actual recruitment numbers per site on 'Projected vs Actual by Site' tab.
5. OPTIONAL Modify number of sites/timeline and add number of final follow ups completed to track completed patients on 'Final follow up_completed' tab.
NOTES:
This recruitment tracker has been set up for a maximum of 60 sites. Please contact sian.irvine@ed.ac.uk for 1:1 help if your study has >60 sites.
Any additional study specific calaculations/tracking should be added on new tabs.
Comments can be hidden to retain instructions for later reference (right click: Show/hide comments).
Please contact sian.irvine@ed.ac.uk or kat.oatey@ed.ac.uk if you have any questions.
Note on E2: Sîan Irvine: Add recruitment total here. All percentage recruitments are linked to this total.
Note on A4: IRVINE Sîan: Add/delete appropriate project milestones. Some of these will be on the grant.
Note on B4: Sîan Irvine: Only dates specified on the grant should be added in this column. Grey out or add 'Not specified' for any milestones not given.
Note on C4: Sîan Irvine: Only add extension dates agreed with the funder.
Note on D4: Sîan Irvine: Add your real initial estimate and start dates. This may be different to those specified on the grant.
Note on E4: Sîan Irvine: Can be used to estimate an extension not yet agreed with funder.
Note on K10: Sîan Irvine: Linked to trial name to automatically populate graph title.
Note on AE10: IRVINE Sîan: Right click on graph>Select Data and check or uncheck boxes to change which of the data lines are visible on the graph
Note on I11: IRVINE Sîan: Add project milestones from the table to the left. Denote actual and estimated date of recruitment milestones using orange/green/blue/grey.
Note on K11: Sîan Irvine: Automatically entered based on ' Grant Projected Recruitment' tab entries.
Note on P11: Sîan Irvine: Automatically entered based on 'Actual Recruitment by Site' tab entries. Drag column down to add additional month.
Note on W11: Sîan Irvine: Automatically entered based on 'Follow Up' tab entries. Drag column down to add additional month.
Note on Y11: Sîan Irvine: Number of withdrawn patients per site can be tracked in 'Follow Up' tab. You will need to track this over time based on eCRF information.
Note on J12: Sîan Irvine: Dates on other tabs are linked to this column. If cells have an error, click '=' then click on this cell, press enter, and drag cells on appropriate tab to fix.
Note on M12: Sîan Irvine: Automatically entered based on 'Projected Feasibility Recruitment' tab entries.

## Gantt Chart
[Trial Name]
Phase | SET-UP | [5 empty] | RECRUITMENT | [31 empty] | FOLLOW UP |  |  | CLOSURE (6 Months)
Actual/Adjusted estimate | SET-UP | [8 empty] | RECRUITMENT | [31 empty] | FOLLOW UP |  |  | CLOSURE (6 Months)
Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
MILESTONES | Jul-202x | Aug-202x | Sep-202x | Oct-202x | Nov-202x | Dec-202x | Jan-202x | Feb-202x | Mar-202x | Apr-202x | May-202x | Jun-202x | Jul-202x | Aug-202x | Sep-202x | Oct-202x | Nov-202x | Dec-202x | Jan-202x | Feb-202x | Mar-202x | Apr-202x | May-202x | Jun-202x | Jul-202x | Aug-202x | Sep-202x | Oct-202x | Nov-202x | Dec-202x | Jan-202x | Feb-202x | Mar-202x | Oct-202x | Nov-202x | Dec-202x | Jan-202x | Feb-202x | Mar-202x | Apr-202x | May-202x | Jun-202x | Jul-202x | Aug-202x | Sep-202x | Oct-202x | Nov-202x | Dec-202x | Jan-202x | Feb-202x | Mar-202x
FUNDER START DATE & DURATION: xx months commencing [Grant start date]
FUNDER MILESTONES
Stop/Go criteria: xx
Milestone 1: xx
Milestone 2: xx
Study Documents
Protocol development
Study Documentation Set Submitted to Sponsor
Sponsor review & Risk Assessment
* TSC and DMC membership & Charter
Submit protocol for publication
Database Development
CRF Content
ECTU Development
Testing
Validations
Reports and Queries finalised
Training Materials
Sponsor Approval (if applicable)
APPROVALS
Ethics, Application and support documentation
NRS/HRA Prepare OID
Registration of study eg. ISRCTN
Portfolio adoption
SITE SET UP
Contracts (drug supply, funder, sites)
Complete Set up of TMF/ISF
Prepare training for SIV Videos education materials
Formal trial opening/SIVs undertaken
RECRUITMENT
Recruitment start/FPFV
50% Recruitment
100% Recruitment/Recruitment end date (LPFV)
FOLLOW UP/CLOSURE
LPLV/Final Follow up
Site Close Out
MEETINGS & COMMUNICATION
Trial Steering Committee
Data Monitoring Committee
TMG/PMG Meetings
Funder Reports
DATA COLLECTION & ANALYSIS
Stats Analysis Plan
Data Cleaning
Database Lock
Statistical Analysis
Stats Report to CI
DISSEMINATION
Submit protocol for publication
Draft Final Report
Primary Manuscipt & Conferences
Archiving
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
Estimate
Actual/Adjusted estimate
Note on A5: Sîan Irvine: Add any grant milestones and study specific actions.
Note on B61: Sîan Irvine: Add pattern by right clicking cell> Format Cells>Fill>Pattern Style

## Projected Feasibility Recruited
Site not open
Recruitment suspended
| 17 | Best recruitment total of the month
[Trial Name] Projected Recruitment from Feasibility/Site Agreement
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no}
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | Total per month | Cumulative total | Cumulative total (%)
7 | Jan 202X | [60 empty] | 0 | 0 | 0%
8 | Feb 202X | 1 | 1 | 1 | [57 empty] | 3 | 3 | 1%
9 | Mar 202X | 1 | 1 | 1 | 1 | 0 | 0 | [54 empty] | 4 | 7 | 2.333%
10 | Apr 202X | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | [52 empty] | 5 | 12 | 4%
11 | May 202X | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [52 empty] | 7 | 19 | 6.333%
12 | Jun 202X | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | [52 empty] | 9 | 28 | 9.333%
13 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 38 | 12.67%
14 | Aug 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 49 | 16.33%
15 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 59 | 19.67%
16 | Oct 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 70 | 23.33%
17 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 81 | 27%
18 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 92 | 30.67%
19 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 102 | 34%
20 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 114 | 38%
21 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 125 | 41.67%
22 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 136 | 45.33%
23 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 146 | 48.67%
24 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 156 | 52%
25 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 165 | 55%
26 | Aug 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [52 empty] | 8 | 173 | 57.67%
27 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 183 | 61%
28 | Oct 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 195 | 65%
29 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 207 | 69%
30 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 218 | 72.67%
31 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 228 | 76%
32 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 240 | 80%
33 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 252 | 84%
34 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 264 | 88%
35 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 274 | 91.33%
36 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 283 | 94.33%
37 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 292 | 97.33%
38 | Aug 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [52 empty] | 8 | 300 | 100%
39 | Sep 202X | [60 empty] | 0 | 300 | 100%
40 | Oct 202X | [60 empty] | 0 | 300 | 100%
41 | Nov 202X | [60 empty] | 0 | 300 | 100%
42 | Dec 202X | [60 empty] | 0 | 300 | 100%
43 | Jan 202X | [60 empty] | 0 | 300 | 100%
44 | Feb 202X | [60 empty] | 0 | 300 | 100%
45 | Mar 202X | [60 empty] | 0 | 300 | 100%
| Total per site | 58 | 58 | 57 | 56 | 27 | 15 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  | 100%
| Predicted total recruitment from site agreement/feasibility | 60 | 60 | 55 | 55 | 30 | 20 | 20 | 21
| Predicted recruitment/month | 1.871 | 1.871 | 1.8387 | 1.8667 | 0.9 | 0.5 | 0.51724 | 0.48276 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
COMMENT:
Enter estimated recruitment per site based on site feasibility/site agreement agreed recruitment numbers.
This tab will populate field on the 'Study Overview' and 'Projected vs Actual Site' tabs.
Note on C5: Sîan Irvine: Enter estimates here for each site based on when it is estimated site will open and number they have agreed to recruit.
Note on B8: Sîan Irvine: Change these on 'Study Overview' tab
Note on C47: Sîan Irvine: Cells will automatically highlight red if the projected site total exceeds the total agreed with the site.
Note on B48: Sîan Irvine: Find this in the site agreement/feasibility form. Projected recruitment for each site entered above should not exceed this total.

## Grant Projected recruitment
Site not open
Recruitment suspended
| 17 | Best recruitment total of the month
[Trial Name] Grant Projected Recruitment
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no}
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | Total per month | Cumulative total | Cumulative total (%)
7 | Jan 202X | [60 empty] | 0 | 0 | 0%
8 | Feb 202X | 1 | 1 | 1 | [57 empty] | 3 | 3 | 1%
9 | Mar 202X | 1 | 1 | 1 | 1 | 0 | 0 | [54 empty] | 4 | 7 | 2.333%
10 | Apr 202X | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | [52 empty] | 5 | 12 | 4%
11 | May 202X | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [52 empty] | 7 | 19 | 6.333%
12 | Jun 202X | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | [52 empty] | 9 | 28 | 9.333%
13 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 38 | 12.67%
14 | Aug 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 49 | 16.33%
15 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 59 | 19.67%
16 | Oct 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 70 | 23.33%
17 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 81 | 27%
18 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 92 | 30.67%
19 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 102 | 34%
20 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 114 | 38%
21 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 125 | 41.67%
22 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | [52 empty] | 11 | 136 | 45.33%
23 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 146 | 48.67%
24 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 156 | 52%
25 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 165 | 55%
26 | Aug 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [52 empty] | 8 | 173 | 57.67%
27 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 183 | 61%
28 | Oct 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 195 | 65%
29 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 207 | 69%
30 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | [52 empty] | 11 | 218 | 72.67%
31 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | [52 empty] | 10 | 228 | 76%
32 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 240 | 80%
33 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 252 | 84%
34 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 264 | 88%
35 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | [52 empty] | 10 | 274 | 91.33%
36 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 283 | 94.33%
37 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 292 | 97.33%
38 | Aug 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | [53 empty] | 8 | 300 | 100%
39 | Sep 202X | [60 empty] | 0 | 300 | 100%
40 | Oct 202X | [60 empty] | 0 | 300 | 100%
41 | Nov 202X | [60 empty] | 0 | 300 | 100%
42 | Dec 202X | [60 empty] | 0 | 300 | 100%
43 | Jan 202X | [60 empty] | 0 | 300 | 100%
44 | Feb 202X | [60 empty] | 0 | 300 | 100%
45 | Mar 202X | [60 empty] | 0 | 300 | 100%
| Total per site | 58 | 58 | 57 | 56 | 27 | 15 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  | 100%
| Predicted recruitment/month | 1.871 | 1.871 | 1.8387 | 1.8667 | 0.9 | 0.5 | 0.51724 | 0.5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
COMMENT:
This tab is optional depending on the detail of estimated recruitment given by your funder.
Enter estimated recruitment per site based on grant milestones/funder given estimates.
Do not complete detail by site if this is not given to you by your funder. Add milestones such as 50% or 100% recruitment' into the 'Total' if you have given dates to achieve this from the funder.
This tab will populate field on the 'Study Overview' and 'Projected vs Actual Site' tabs.
Note on C5: Sîan Irvine: Enter estimates here for each site based on funding bidy estimates. If funding body is not this speciific, leave empty.
Note on C6: Sîan Irvine: Linked to 'Projected Feasibility Recruited ' tab
Note on BK7: Sîan Irvine: Add 50% milestone, for example, here if this is the level of detail given by your funder.
Note on B8: Sîan Irvine: Change these on 'Study Overview' tab

## Actual Recruitment by Site
Site not open
Recruitment suspended
| 17 | Best recruitment total of the month |  |  |  | 3
[Trial Name] Actual Recruitment
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | Total per month | Cumulative total | Cumulative total (%)
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name]
7 | Jan 202X | [60 empty] | 0 | 0 | 0%
8 | Feb 202X | [60 empty] | 0 | 0 | 0%
9 | Mar 202X | [60 empty] | 0 | 0 | 0%
10 | Apr 202X | 1 | 3 | 2 | 1 | [56 empty] | 7 | 7 | 2.333%
11 | May 202X | [60 empty] | 0 | 7 | 2.333%
12 | Jun 202X | [60 empty] | 0 | 7 | 2.333%
13 | Jul 202X | [60 empty] | 0 | 7 | 2.333%
14 | Aug 202X | [60 empty] | 0 | 7 | 2.333%
15 | Sep 202X | [60 empty] | 0 | 7 | 2.333%
16 | Oct 202X | [60 empty] | 0 | 7 | 2.333%
17 | Nov 202X | [60 empty] | 0 | 7 | 2.333%
18 | Dec 202X | [60 empty] | 0 | 7 | 2.333%
19 | Jan 202X | [60 empty] | 0 | 7 | 2.333%
20 | Feb 202X | [60 empty] | 0 | 7 | 2.333%
21 | Mar 202X | [60 empty] | 0 | 7 | 2.333%
22 | Apr 202X | [60 empty] | 0 | 7 | 2.333%
23 | May 202X | [60 empty] | 0 | 7 | 2.333%
24 | Jun 202X | [60 empty] | 0 | 7 | 2.333%
25 | Jul 202X | [60 empty] | 0 | 7 | 2.333%
26 | Aug 202X | [60 empty] | 0 | 7 | 2.333%
27 | Sep 202X | [60 empty] | 0 | 7 | 2.333%
28 | Oct 202X | [60 empty] | 0 | 7 | 2.333%
29 | Nov 202X | [60 empty] | 0 | 7 | 2.333%
30 | Dec 202X | [60 empty] | 0 | 7 | 2.333%
31 | Jan 202X | [60 empty] | 0 | 7 | 2.333%
32 | Feb 202X | [60 empty] | 0 | 7 | 2.333%
33 | Mar 202X | [60 empty] | 0 | 7 | 2.333%
34 | Apr 202X | [60 empty] | 0 | 7 | 2.333%
35 | May 202X | [60 empty] | 0 | 7 | 2.333%
36 | Jun 202X | [60 empty] | 0 | 7 | 2.333%
37 | Jul 202X | [60 empty] | 0 | 7 | 2.333%
38 | Aug 202X | [60 empty] | 0 | 7 | 2.333%
39 | Sep 202X | [60 empty] | 0 | 7 | 2.333%
40 | Oct 202X | [60 empty] | 0 | 7 | 2.333%
41 | Nov 202X | [60 empty] | 0 | 7 | 2.333%
42 | Dec 202X | [60 empty] | 0 | 7 | 2.333%
43 | Jan 202X | [60 empty] | 0 | 7 | 2.333%
44 | Feb 202X | [60 empty] | 0 | 7 | 2.333%
45 | Mar 202X | [60 empty] | 0 | 7 | 2.333%
| Total per site | 1 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  | 2.333%
| Predicted total recruitment | 60 | 60 | 55 | 55 | 30 | 20 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SATO/recruitment start date | 2023-03-29
| Days open | 615 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629 | 45629
| Average patient/ month | 0.04878 | 0.0019724 | 0.001315 | 0.00065748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
| Withdrawn | 1 | 0 | 0 | 0
| %Withdrawn (Drop out rate) | 100% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0%
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
COMMENT:
Enter real recruitment data here from the eCRF.
This tab will populate field on the 'Study Overview' and 'Projected vs Actual Site' tabs.
Graphs and data here may be useful for Funding Reports, CI meetings or site newsletters.
Note on C6: Sîan Irvine: Linked to 'Projected Feasibility Recruited ' tab
Note on B8: Sîan Irvine: Change these on 'Study Overview' tab
Note on F11: Sîan Irvine: Top recruiter of month is automatically highlighted in green.
Note on B48: Sian Irvine: From site agreement/feasibility - these are linked to 'Projected recruitment by site' page
Note on B50: IRVINE Sîan: When recruitment is over, substitute "Today()" in formula for actual recruitment end date
Note on B53: Sîan Irvine: % of patients withdrawn per site gives the dropout rate for the study. These will highlight yellow if over 15% and red if over 50%.

## Projected vs Actual by Site
[Trial Name] Tracked/Cumulative total Projected vs Actual recruitment per site
| Site | Fife
|  | Fife Tracked Recruitment | [5 empty] | Fife Cumulative Recruitment
Project Month |  | Projected Grant | Projected by Feasibility | Actual | Adjusted/Extension | Project Month |  | Projected Grant | Projected by Feasibility | Actual | Adjusted/Extension
7 | Jan 202X | 0 | 0 | 0 | 0 | 7 | Jan 202X | 0 | 0 | 0 | 0
8 | Feb 202X | 1 | 1 | 0 | 0 | 8 | Feb 202X | 1 | 1 | 0 | 0
9 | Mar 202X | 1 | 1 | 0 | 0 | 9 | Mar 202X | 2 | 2 | 0 | 0
10 | Apr 202X | 1 | 1 | 3 | 1 | 10 | Apr 202X | 3 | 3 | 3 | 1
11 | May 202X | 1 | 1 | 0 | 1 | 11 | May 202X | 4 | 4 | 3 | 2
12 | Jun 202X | 2 | 2 | 0 | 1 | 12 | Jun 202X | 6 | 6 | 3 | 3
13 | Jul 202X | 2 | 2 | 0 | 1 | 13 | Jul 202X | 8 | 8 | 3 | 4
14 | Aug 202X | 2 | 2 | 0 | 2 | 14 | Aug 202X | 10 | 10 | 3 | 6
15 | Sep 202X | 2 | 2 | 0 | 2 | 15 | Sep 202X | 12 | 12 | 3 | 8
16 | Oct 202X | 2 | 2 | 0 | 2 | 16 | Oct 202X | 14 | 14 | 3 | 10
17 | Nov 202X | 2 | 2 | 0 | 2 | 17 | Nov 202X | 16 | 16 | 3 | 12
18 | Dec 202X | 2 | 2 | 0 | 2 | 18 | Dec 202X | 18 | 18 | 3 | 14
19 | Jan 202X | 2 | 2 | 0 | 2 | 19 | Jan 202X | 20 | 20 | 3 | 16
20 | Feb 202X | 2 | 2 | 0 | 2 | 20 | Feb 202X | 22 | 22 | 3 | 18
21 | Mar 202X | 2 | 2 | 0 | 2 | 21 | Mar 202X | 24 | 24 | 3 | 20
22 | Apr 202X | 2 | 2 | 0 | 2 | 22 | Apr 202X | 26 | 26 | 3 | 22
23 | May 202X | 2 | 2 | 0 | 2 | 23 | May 202X | 28 | 28 | 3 | 24
24 | Jun 202X | 2 | 2 | 0 | 2 | 24 | Jun 202X | 30 | 30 | 3 | 26
25 | Jul 202X | 2 | 2 | 0 | 2 | 25 | Jul 202X | 32 | 32 | 3 | 28
26 | Aug 202X | 2 | 2 | 0 | 2 | 26 | Aug 202X | 34 | 34 | 3 | 30
27 | Sep 202X | 2 | 2 | 0 | 2 | 27 | Sep 202X | 36 | 36 | 3 | 32
28 | Oct 202X | 2 | 2 | 0 | 2 | 28 | Oct 202X | 38 | 38 | 3 | 34
29 | Nov 202X | 2 | 2 | 0 | 2 | 29 | Nov 202X | 40 | 40 | 3 | 36
30 | Dec 202X | 2 | 2 | 0 | 2 | 30 | Dec 202X | 42 | 42 | 3 | 38
31 | Jan 202X | 2 | 2 | 0 | 2 | 31 | Jan 202X | 44 | 44 | 3 | 40
32 | Feb 202X | 2 | 2 | 0 | 2 | 32 | Feb 202X | 46 | 46 | 3 | 42
33 | Mar 202X | 2 | 2 | 0 | 2 | 33 | Mar 202X | 48 | 48 | 3 | 44
34 | Apr 202X | 2 | 2 | 0 | 2 | 34 | Apr 202X | 50 | 50 | 3 | 46
35 | May 202X | 2 | 2 | 0 | 2 | 35 | May 202X | 52 | 52 | 3 | 48
36 | Jun 202X | 2 | 2 | 0 | 2 | 36 | Jun 202X | 54 | 54 | 3 | 50
37 | Jul 202X | 2 | 2 | 0 | 2 | 37 | Jul 202X | 56 | 56 | 3 | 52
38 | Aug 202X | 2 | 2 | 0 | 2 | 38 | Aug 202X | 58 | 58 | 3 | 54
39 | Sep 202X | 0 | 0 | 0 | 2 | 39 | Sep 202X | 58 | 58 | 3 | 56
40 | Oct 202X | 0 | 0 | 0 | 2 | 40 | Oct 202X | 58 | 58 | 3 | 58
41 | Nov 202X | 0 | 0 | 0 | 0 | 41 | Nov 202X | 58 | 58 | 3 | 58
42 | Dec 202X | 0 | 0 | 0 | 0 | 42 | Dec 202X | 58 | 58 | 3 | 58
43 | Jan 202X | 0 | 0 | 0 | 0 | 43 | Jan 202X | 58 | 58 | 3 | 58
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Note on C5: Sîan Irvine: Select site from drop down menu to change graphs.
Note on R7: Sîan Irvine: Right click on graph>Select Data and check or uncheck boxes to change which of the data lines are visible on the graph
Note on K9: Sîan Irvine: Top line is automatically entered from either 'Projected Recruitment by Site' or 'Actual Recruitment per Site' tabs. Consquent line formulas add the previous line to give a cumulative total Projected/Actual recruitment total.
COMMENT:
Do not edit this tab unless to edit site names, add more sites or amend the timeline.

## Adjusted Projection by Site
Site not open
Recruitment suspended
[Trial Name] Adjusted Extension Recruitment
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no}
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | Total per month | Cumulative total | Cumulative total (%)
7 | Jan 202X | 6 | [59 empty] | 6 | 6 | 2%
8 | Feb 202X | [60 empty] | 0 | 6 | 2%
9 | Mar 202X | [60 empty] | 0 | 6 | 2%
10 | Apr 202X | 1 | 1 | 1 | [57 empty] | 3 | 9 | 3%
11 | May 202X | 1 | 1 | 1 | 1 | 0 | 0 | [54 empty] | 4 | 13 | 4.333%
12 | Jun 202X | 1 | 1 | 1 | 1 | 1 | 0 | 0 | [53 empty] | 5 | 18 | 6%
13 | Jul 202X | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [52 empty] | 7 | 25 | 8.333%
14 | Aug 202X | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | [52 empty] | 8 | 33 | 11%
15 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 44 | 14.67%
16 | Oct 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 54 | 18%
17 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 65 | 21.67%
18 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 75 | 25%
19 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 86 | 28.67%
20 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 98 | 32.67%
21 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 107 | 35.67%
22 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 119 | 39.67%
23 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 131 | 43.67%
24 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 141 | 47%
25 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 152 | 50.67%
26 | Aug 202X | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | [52 empty] | 10 | 162 | 54%
27 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 171 | 57%
28 | Oct 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [52 empty] | 8 | 179 | 59.67%
29 | Nov 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 188 | 62.67%
30 | Dec 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 200 | 66.67%
31 | Jan 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 212 | 70.67%
32 | Feb 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 224 | 74.67%
33 | Mar 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 233 | 77.67%
34 | Apr 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 245 | 81.67%
35 | May 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 257 | 85.67%
36 | Jun 202X | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | [52 empty] | 12 | 269 | 89.67%
37 | Jul 202X | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | [52 empty] | 11 | 280 | 93.33%
38 | Aug 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 289 | 96.33%
39 | Sep 202X | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | [52 empty] | 9 | 298 | 99.33%
40 | Oct 202X | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [52 empty] | 8 | 306 | 102%
41 | Nov 202X | [60 empty] | 0 | 306 | 102%
42 | Dec 202X | [60 empty] | 0 | 306 | 102%
43 | Jan 202X | [60 empty] | 0 | 306 | 102%
44 | Feb 202X | [60 empty] | 0 | 306 | 102%
45 | Mar 202X | [60 empty] | 0 | 306 | 102%
| Total per site | 64 | 58 | 57 | 56 | 27 | 15 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 |  | 102%
| Predicted total recruitment from site agreement/feasibility | 60 | 60 | 55 | 55 | 30 | 20 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Predicted recruitment/month | 2 | 1.871 | 1.8387 | 1.8667 | 0.9 | 0.5 | 0.51724 | 0.5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
Note on C5: Sîan Irvine: Enter estimates here for each site based on when it is estimated site will open and number they have agreed to recruit.
Note on C6: Sîan Irvine: Linked to 'Projected Feasibility Recruited ' tab
Note on B8: Sîan Irvine: Change these on 'Study Overview' tab
Note on C47: Sîan Irvine: Cells will automatically highlight red if the projected site total exceeds the total agreed with the site.
Note on B48: Sîan Irvine: Find this in the site agreement/feasibility form. Projected recruitment for each site entered above should not exceed this total.
COMMENT:
This tab is OPTIONAL and can be used to estimate an adjusted timeline in the event of a delayed start or suspension to recruitment, for example.
This tab will populate field on the 'Study Overview' and 'Projected vs Actual Site' tabs.
Graphs and data here may be useful for requesting a funding extension or internal meetings.

## Final follow up_completed
No follow ups due
Recruitment suspended
[Trial Name] Final Follow Up Completed
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | Final Follow Ups per month | Cumulative total
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name]
7 | Jan 202X | [60 empty] | 0 | 0
8 | Feb 202X | [60 empty] | 0 | 0
9 | Mar 202X | [60 empty] | 0 | 0
10 | Apr 202X | [60 empty] | 0 | 0
11 | May 202X | [60 empty] | 0 | 0
12 | Jun 202X | [60 empty] | 0 | 0
13 | Jul 202X | [60 empty] | 0 | 0
14 | Aug 202X | [60 empty] | 0 | 0
15 | Sep 202X | [60 empty] | 0 | 0
16 | Oct 202X | [60 empty] | 0 | 0
17 | Nov 202X | [60 empty] | 0 | 0
18 | Dec 202X | [60 empty] | 0 | 0
19 | Jan 202X | [60 empty] | 0 | 0
20 | Feb 202X | [60 empty] | 0 | 0
21 | Mar 202X | [60 empty] | 0 | 0
22 | Apr 202X | [60 empty] | 0 | 0
23 | May 202X | [60 empty] | 0 | 0
24 | Jun 202X | [60 empty] | 0 | 0
25 | Jul 202X | [60 empty] | 0 | 0
26 | Aug 202X | [60 empty] | 0 | 0
27 | Sep 202X | [60 empty] | 0 | 0
28 | Oct 202X | [60 empty] | 0 | 0
29 | Nov 202X | [60 empty] | 0 | 0
30 | Dec 202X | [60 empty] | 0 | 0
31 | Jan 202X | [60 empty] | 0 | 0
32 | Feb 202X | [60 empty] | 0 | 0
33 | Mar 202X | [60 empty] | 0 | 0
34 | Apr 202X | [60 empty] | 0 | 0
35 | May 202X | [60 empty] | 0 | 0
36 | Jun 202X | [60 empty] | 0 | 0
37 | Jul 202X | [60 empty] | 0 | 0
38 | Aug 202X | [60 empty] | 0 | 0
39 | Sep 202X | [60 empty] | 0 | 0
40 | Oct 202X | [60 empty] | 0 | 0
41 | Nov 202X | [60 empty] | 0 | 0
42 | Dec 202X | [60 empty] | 0 | 0
43 | Jan 202X | [60 empty] | 0 | 0
44 | Feb 202X | [60 empty] | 0 | 0
45 | Mar 202X | [60 empty] | 0 | 0
| Total per site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Remaining final follow ups | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Withdrawn | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % pts withdrawn (Drop out Rate | 100% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| % Completed pts | 100% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
COMMENT:
This tab is OPTIONAL. Delete if not required.
This tab can be useful in tracking that all sites have completed LPLV.
Entries here contribute to the 'Completed patients' numbers in the 'Study Overview' tab.
Number of withdrawn patients per site can also be recorded here.
Note on C4: Sîan Irvine: Enter estimates here for each site based on when it is estimated site will open and number they have agreed to recruit.
Note on C5: Sîan Irvine: Linked to 'Projected Feasibility Recruited ' tab
Note on B7: Sîan Irvine: Change these on 'Study Overview' tab
Note on B48: Sîan Irvine: Linked to Actual Recruitment by Site tab

## Screening_Washout
Site not open
Recruitment suspended
[Trial Name] Screening/Washout
|  | 1 | 2 | 3 | 4 | 5 | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | [Site no} | Total per month | Cumulative total
Project Month |  | Edinburgh (RIE) | Fife | GGC | Aberdeen | Inverness | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name] | [Site name]
7 | Jan 202X | [60 empty] | 0 | 0
8 | Feb 202X | [60 empty] | 0 | 0
9 | Mar 202X | [60 empty] | 0 | 0
10 | Apr 202X | [60 empty] | 0 | 0
11 | May 202X | [60 empty] | 0 | 0
12 | Jun 202X | [60 empty] | 0 | 0
13 | Jul 202X | [60 empty] | 0 | 0
14 | Aug 202X | [60 empty] | 0 | 0
15 | Sep 202X | [60 empty] | 0 | 0
16 | Oct 202X | [60 empty] | 0 | 0
17 | Nov 202X | [60 empty] | 0 | 0
18 | Dec 202X | [60 empty] | 0 | 0
19 | Jan 202X | [60 empty] | 0 | 0
20 | Feb 202X | [60 empty] | 0 | 0
21 | Mar 202X | [60 empty] | 0 | 0
22 | Apr 202X | [60 empty] | 0 | 0
23 | May 202X | [60 empty] | 0 | 0
24 | Jun 202X | [60 empty] | 0 | 0
25 | Jul 202X | [60 empty] | 0 | 0
26 | Aug 202X | [60 empty] | 0 | 0
27 | Sep 202X | [60 empty] | 0 | 0
28 | Oct 202X | [60 empty] | 0 | 0
29 | Nov 202X | [60 empty] | 0 | 0
30 | Dec 202X | [60 empty] | 0 | 0
31 | Jan 202X | [60 empty] | 0 | 0
32 | Feb 202X | [60 empty] | 0 | 0
33 | Mar 202X | [60 empty] | 0 | 0
34 | Apr 202X | [60 empty] | 0 | 0
35 | May 202X | [60 empty] | 0 | 0
36 | Jun 202X | [60 empty] | 0 | 0
37 | Jul 202X | [60 empty] | 0 | 0
38 | Aug 202X | [60 empty] | 0 | 0
39 | Sep 202X | [60 empty] | 0 | 0
40 | Oct 202X | [60 empty] | 0 | 0
41 | Nov 202X | [60 empty] | 0 | 0
42 | Dec 202X | [60 empty] | 0 | 0
43 | Jan 202X | [60 empty] | 0 | 0
44 | Feb 202X | [60 empty] | 0 | 0
45 | Mar 202X | [60 empty] | 0 | 0
| Total per site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Average no. pts screened / month | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Successful screening/washout rate (%) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TM-T36 ECTU Recruitment Project Plan Tracker TEMPLATE v2.0 31/07/202
Updated xx/xx/202x
COMMENT:
This tab is OPTIONAL. Delete if not required.
This tab can be used to document patients screened, in the absence of a REDcap screening log, or number of patients recruited to washout but not yet randomised.
Note on C4: Sîan Irvine: Enter estimates here for each site based on when it is estimated site will open and number they have agreed to recruit.
Note on C5: Sîan Irvine: Linked to 'Projected Feasibility Recruited ' tab
Note on B7: Sîan Irvine: Change these on 'Study Overview' tab