This is not an exhaustive list but for guidance purposes only.  Delegation of a task may be required, ability to delegate  will depend on the complexity of the task, the support available for the specific trial and competence of individuals. Delegation of a task must always be approved by a Senior TM.

| TASKS | Activity required to complete task | Appropriate level of staff |
| --- | --- | --- |
| Preparation of Protocol |  | COMBINED - see below |
|  | Writing and working with CI/Statistician to create protocol | TM |
|  | Formatting of protocol and addition of pre-collected information | ATM/TMSO |
| Preparation of PIS, Consent, letters |  | COMBINED - see below |
|  | Addition of pre-collected information in forms | ATM/TMSO |
|  | Preparation of PIS, consent, letters | TM/ATM |
| Preparation and submission of ethics, R&D & amendments |  | COMBINED - see below |
|  | Addition of pre-collected information in forms | TMSO |
|  | Preparation of Ethics and R&D forms | ATM |
|  | Review and submission | TM |
|  | Non-substantial amendments to documentation, preparing local versions | ATM |
|  | Substantial amendments to documentation or creation of new documents | TM |
|  | Addition of new sites to IRAS and SSI form completions | ATM |
| MHRA and ARSAC application |  | TM |
| Preparation of TMF & ISF |  | COMBINED - see below |
|  | Adaptation of existing template logs (e.g. patient ID logs, screening logs etc.) | TM |
|  | Obtaining essential documents for TMF and ISF (e.g. accreditations, lab ranges, CVs and GCP & ARSAC licences, delegation log) & keeping them up to date | TMSO |
|  | Creation of IMP documentation – accountability logs, destruction records | TM |
| IMP accountability & planning |  | COMBINED - see below |
|  | IMP campaigns (calculating how much is needed etc.) | TM |
|  | Drug accountability checking | ATM? |
|  | Managing and ordering IMP when stocks are low | ATM |
| Database development and data management |  | COMBINED - see below |
|  | Query generation | TM |
|  | Testing & validating the database | ATM/TMSO |
|  | Database amendments/revisions requests | TM / ATM |
|  | Preparation of unblinding procedure documents | TM /ATM |
|  | Formatting CRFs | TMSO |
|  | Source data plan | ATM |
|  | Generate dataset list | TM / ATM |
|  | Sites with long-running data queries, recurrent problems | TM |
|  | Data oversight | TM |
|  | Queries with follow-up - ECTU to participant and vice versa | Should be qualified clinical |
|  | Queries with follow-up - ECTU to site or vice versa | ATM/TMSO |
| Preparation of co-sponsorship and template site agreement / SLAs |  | TM |
|  | Following up on outstanding contract amendments | TM / ATM |
|  | Adding site specific info to template site agreement | ATM / TMSO |
|  | Preparation of service level agreements (e.g. drug supply, other HEIs, technical agreements, SLAs within university) | TM |
| Sites | Site initiation visit and completion of SIV report | TM |
|  | Completion of Sponsor Authorisation To Open | TM |
|  | Site monitoring | Variable (usually sponsor responsibility) |
|  | Recruitment uploads | COMBINED - see below |
|  | Uploads to ATR (ACCORD tracker) | TMSO |
|  | Uploads to NIHR portfolio (if an adopted multicentre study) | TMSO |
|  | Managing Recruitment and develop recruitment strategies | TM/ ATM / TMSO |
|  | Generating ACCORD ISF/TMF tracker | TM |
|  | Maintaining TMF & ACCORD ISF/TMF tracker | TMSO |
| Document / stock management |  | COMBINED - see below |
|  | Version control | TM/ ATM / TMSO |
|  | Site Newsletters - creation | ATM/ TMSO |
|  | Site Newsletters - review and approval | TM |
|  | Site Newsletters - circulation | TMSO |
|  | Circulation of approved documents to sites & tracking | TMSO |
|  | Send thank you letters, certificates and vouchers | TMSO |
|  | Preparation of packs, kits and printing | TMSO |
|  | Send out packs and materials to sites on request | TMSO |
|  | Adding users to live database | ATM / TMSO |
|  | Dealing with trial specific post - Open questionnaires | TMSO |
| Oversight & reporting |  | COMBINED - see below |
|  | Deviations - collecting and sending to ACCORD (if sent to ECTU first) | TMSO |
|  | Oversight groups - establishing charter | TM |
|  | Arranging TSC and DMC Meetings & minuting meetings | TMSO |
|  | Preparing Oversight Committee reports | TM (delegating tasks to ATM for information gathering) |
|  | Arranging and minuting TMGs | ATM/TMSO |
|  | Prepare and supply the DSUR to the Sponsor | TM |
|  | Drafting of safety progress reports | ATM |
|  | Drafting of end of trial notification to REC, R&D, MHRA | ATM |
|  | Completion of funder progress reports | TM (delegating tasks to ATM for information gathering) |
|  | contribute to manuscript | TM |
| Tracking & procedures |  | COMBINED - see below |
|  | SOPs and WPDs (if applicable) CREATION / REVIEW | TM (delegated) |
|  | Specification of tracking documents | TM |
|  | Preparation of tracking documents | ATM |
|  | Tracking and checking consents which are received in ECTU | TMSO |
|  | Log dispatch, receipt and reconciliation of goods | TMSO |
| Oversight and management of funding |  | COMBINED - see below |
|  | Extension requests | TM |
|  | Trial recovery plans | TM |
|  | Cross-check payments on Webfirst and financial reconciliations | TM |
|  | Submit invoices to admin and chase up if outstanding | TMSO |
|  | Send out invoice requests to site | TMSO (with TM approval before sending) |
| Archiving |  | COMBINED (TM oversight) |
| Study website & advertising |  | COMBINED (TM oversight) |
|  | Study website content creation | ATM |
|  | Website maintenance | TMSO |
|  | Trial promotion / dissemination plans | ALL (TM oversight) |
|  | Arrange dissemination events | ATM / TMSO |

<<Remove this Page from Study Specific Version>>

| Document Revision History |  |  |
| --- | --- | --- |
| Version No | Date | Summary of Revisions |
| 1.0 | 16 Jun 2022 | Initial creation/New document |
| 1.0 | 28 May 2024 | No amendments required |